## TeamRegister
Individuals/Roles | Project Manager | System Architecture | Team Leader | Scrum Master | Design Engineer
Quinten | X |  |  |  | X
Kareem |  |  | X |  | X
Joseph |  | X |  |  | X
Mahsa |  |  |  | X | X
Arjun |  |  |  |  | X
Deniz |  |  |  |  | X
Naheed |  |  |  |  | X
Anshid |  |  |  |  | X

## StakeholderRegister
ID | First Name | Last Name | E-mail | Organization | Sub organisation | Role | Power | Interest
1 | Rene | van de Molengraft | m.j.g.v.d.molengraft@tue.nl | TU/e | Tech United | Project Sponsor and Technical Consultant | High | High
2 | Erjen | Lefeber | a.a.j.lefeber@tue.nl | TU/e |  | Project Sponsor | High | High
3 |  |  | techunited@tue.nl | TU/e | Tech United | User of System | Low | High
4 |  |  |  | RoboCup | Middle Sized League | User of System and Rule Maker | High | Low
5 | Ruben | Beumer | r.m.beuner@tue.nl | TU/e | Tech United | Technical Consultant | Low | High
6 | Ivan | Kolodkvo | i.kolodko@tue.nl | TU/e | Tech United | Technical Consultant | Low | High
7 | Danny | Hameeteman | d.m.j.hameeteman@tue.nl | RoboCup | Middle Sized League | Referee | Low | High

## DecisionRegister
ID | Decision Details | Impact | Proposed Date | Proposed By | Status | Approved By | Date
1 | Set the scope of the project to only focus on two rules: Illegal attack and Defense (RC-12.3.4 & RC-12.3.5) and who touched the ball the last time (FL-15, FL-16 and FL-17). | Set the project scope. | 2024-02-19 | Team | Approved | Team (majority vote) and René ("if you as a team agree, I agree") | 2024-02-19
2 | Set the scope of the project to only focus on one rule: who touched the ball the last time after the ball is out of play and communicate this to the referee. | Change of project scope | 2024-02-23 | Team | Not approved

## ProductBacklog
ID | User story | Size | Priority | Sprint
1 | As a stakeholder, I want to know the risks of the project, so that I better understand the status of the project. | Low | High | 3
2 | As a developer, I want to know the functional requirements of the system, so that I can set up the specifications | Medium | High | 3
3 | As a stakeholder, I want to know the deliverables of this project, so that I know what I get where I paid for. | Low | High | 3
4 | As a developer, I want to know the specifications of the system, so that I know which solutions fit into that. | High | High | 3
5 | As a developer, I want to know how to validate the system, so that I can perform the validation tests. | Low | High | 3
6 | As a developer, I want a feasibility check, so that I know which solution fits best to the specifications. | Medium | Medium | 3
7 | As a referee, I want to know which decision the AutoRef system decided so that it can support me in my decisions. | Low | Low
8 | As a developer, I want to know when the ball is out of play so that I can decide who gets FL-15, 16 and 17. | High | Medium
9 | As a developer, I want to know who applied a force to the ball so that I know who touched the ball the last time. | High | Medium

## RiskRegister
ID | Process Step / component / function | Potential Failure Mode | Potential Failure Effect | Severity1 | Potential Causes | Occurance2 | Current Controls | Detection3 | RPN4 | RPN+ | Action Recommended
Number | What is the process step or component or function? | In what ways can the process step / component / function go wrong or fail? | What is the impact on the end user if the failure mode is not prevented or corrected? | How severe is the effect on the end user? | What causes the process step or component or function to go wrong (i.e., how could the failure mode occur)? | How frequencly is the cause likely to occur? | What are the existing controls that either prevent the failure mode from occuring or detect it if it should occur? | How probable is detection of the failure mode or its cause | Risk priority number calculated as SEV x OCC | RPN with DET | What are the actions for reducting the occurance of the cause or for improving its detection? Provide actions on all high RPNs.
1 | Sensing | Sensors have too low accuracy | Wrong decisions | 4 | Budget limitations, availability of hardware or wrong assumptions | 3 | Set specifications |  | 12 | 0 | Use good sources for assumptions. Create a decision matrix for choosing solution space and hardware.
2 | Bias | Decisions are biased to a certain team | Wrong decisions | 4 | Not tested on other teams | 1 |  |  | 4 | 0 | Make solution independent on specific TURTLEs
3 | Trust | No trust from referees or audience in deicison making | System is not used | 4 | No proof | 2 |  |  | 8 | 0 | Need proof of decions made
4 | Robustness | Wrong measurements because of external factors. | Wrong decisions in other fields | 3 | Different lightning. | 1 |  |  | 3 | 0
5 | Security | Team hack the system | Gives wrong decisions every time | 4 | Hacking | 1 |  |  | 4 | 0
6 | Edge cases | Wrong decisions | Wrong decisions | 2 | Not identifying all edge cases | 4 | Talking with referees |  | 8 | 0 | Tested on real match
7 | Implementation | Implementation takes too long | Whole project is delayed | 3 | Team knowledge too low | 3 |  |  | 9 | 0
8 | Validation and verification | We can not test the system due to other people using the field. | Project delayed. | 3 | Not planning, something else gets in the way of testing. Not the right equipment to verify. | 3 |  |  | 9 | 0
9 | Teamwork | Not working well together | Project delayed. Not making right decisions. | 3 | Stubborness, ego, indecisiveness, different backgrounds and not communicating | 2 |  |  | 6 | 0 | Implementing a communication plan in PMP.
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
1. Severity: Severity of impact of failure event. It is scored on a scale of 1 to 5. A high score is assigned to high-impact events while a low score is assigned to low-impact events.
2. Occurance or Probability: Frequency of occurance of failure event. It is scored on a scale of 1 to 5. A high score is assigned to frequently occuring events while events with low occuraence are assigned a low score.
3. Detection: Ability of process control to detect the occurance of failure events. It is scored on a scale of 1 to 5. A failure event that can be easilty detected by the process control is assigned a low score while a high score is assigned to an inconspicuous event.
4. Risk Priority Number: The overall risk score of an event or failure. It is calculated by multiplying the scores for severity, occurance and detection. An event with a high RPN demands immediate attention while events with lower RPNs are less risky.